## Xmas - Outhouses
ROYAL MAIL XMAS 22 - OUTHOUSES
REFS |  | DETAILS | [5 empty] | SURVEYOR |  |  |  | STATUS |  |  |  | OTHER
SEP REF | L CATON REF | SITE | Type | ADDRESS | Special Events Planner | Site Contact | Comments | PRACTICE | SURVEYOR 1 | SURVEYOR 2 | Previous Surveyor | LEASE START | LEASE EXPIRY | RFS | LDS | COMMENTS
Site 1 | 18 | Norwich MC (Diamond Road - second site) | OUTHOUSE |  | Jasmin Mann | 07841568085 angela.travis@royalmail.com | Site visit undertaken Friday 14th Oct. SOW to Vinci for pricing Mon 17th Oct. Accio returned costs for temporary dock. SOC being finalised. | RLB | Seb Hathaway | Robbie Brindley | Chris Tighe |  |  | 2022-11-14 | 2022-12-31 | Site not yet aquired
Site 2 |  | South Midlands Plant | OUTHOUSE | Northampton HUB/PSC Stobarts Northampton Unit 5 Panattoni Park Weedon Road NORTHAMPTON NN7 4DE | Helen Perry | 07553 367512 mohammad.s.rahman@royalmail.com | PSC Brought back online as part of IA planning, check with SEP whether site kept live for Peak, and whether any ancillary works required. Portakabin scoped, Trios pricing, no water requirements. Price returned awaiting SEP sign off. RFS 24th November - change to plan. | RLB | Andrew Jenkins |  |  |  |  | 2022-11-24 | 2023-01-20
Site 3 | 16 | Leeds Area | OUTHOUSE |  | Anne O'Connor | 07921107332 anne.oconnor1@royalmail.com |  | RLB | Matt Hayter | ABORTED
Site 4 | 31 | Tyneside / Peterlee | OUTHOUSE | Walkers, Stephenson Road, Peterlee, Durham, SR8 5AY | Anne O'Connor | 07921107332 anne.oconnor1@royalmail.com | Started this week, operations happy with works. Few queries from subcontractor. Accio being programmed in. Works going well, on programme, no budget issues - few variations but some omissions. Under budget currently. Bins can be dropped off when ready | RLB | Andrew Jenkins |  |  | 03/10/2022 - picking up keys 5/10/22 |  | 2022-11-01 | 2023-01-31
Site 5 | 2 | East of Scotland Outhouse | OUTHOUSE | Royal Highland Showground | Scott Forsyth | graeme.c.kelly@royalmail.com | SOC dates to be agreed following RLB/RMG meeting today. AECOM meeting TRIOS and Landlord 22/9/22 to discuss Landlord electrical works. Trios have advised they can potentially get works complete for RFS date however will require weekend working and premium on costs. Isolated items may need to be carried out after the RFS date. RMG to confirm exactly what works need done for RFS date. | AECOM | Derek Penny | Scott Graham | Scott Graham | 2022-11-18 | tbc | 2022-11-21 | 2023-01-14
Site 6 | 33 | Medway MC (Rochester) | OUTHOUSE |  | Nicole Menon | gary.ware@royalmail.com 07841570847 | Confirmed not required 1st Sept 2022 | RLB | Seb Hathaway | ABORTED
Site 7 |  | Medway OH (Rochester) | OUTHOUSE |  | Nicole Menon | gary.ware@royalmail.com 07841570847 | Price returned by Vinci. Priced document sent to Paul for approval. PCI drafted to be issued to RLB PD. Awaiting approval before being sent out. PAP drafted (exisiting site?) | RLB | Seb Hathaway | Yvonne Duong |  |  |  | 2022-11-28 | 2023-01-08
Site 8 | 1 | Bristol MC | OUTHOUSE |  | Alan Nicholls | 07802 928683 robert.j.paterson@royalmail.com | NO SITE YET | KKS | Glyn Jones |  |  |  |  | 2022-11-01 | 2023-01-30
Site 9 |  | HWDC | OUTHOUSE |  | Andy Martin | stephen.hibbert@royalmail.com |  | KKS | Glyn Jones | Not required
Site 10 |  | Buckingham DO | OUTHOUSE |  |  |  | Site visit undertaken 10th Oct. SOW to Vinci for pricing 13th Oct. | RLB | Seb Hathaway | Carolina Lopato
Note on B4: Paul McGouran: Applies to OH, Parking, VOC sites
Note on C5: Paul McGouran: Might be a temp unit / Outhouse - confirm with SEP
Note on O6: Paul McGouran: Amended in line with HP instruction to AJ
Note on O11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Amended as per agenda issued

## Xmas - Internals
ROYAL MAIL XMAS 22 - INTERNALS | [15 empty] | Updated 12th September
REFS |  | DETAILS | [5 empty] | SURVEYOR |  |  |  | STATUS |  |  |  | OTHER
SEP REF | L CATON REF | SITE | Type | ADDRESS | Special Events Planner | Site Contact | Comments | PRACTICE | SURVEYOR 1 | SURVEYOR 2 | Previous Surveyor | LEASE START | LEASE EXPIRY | RFS | LDS | COMMENTS
Internals Site 1 | 2 | East of Scotland Outhouse | Internal (Existing Site) | Edinburgh Mail Centre, 11 Cultins Road, EDINBURGH, EH11 4YY | Scott Forsyth | GRAEME.C.KELLY@ROYALMAIL.COM | Duplicate of outhouse works (Site 5) | AECOM | Derek Penny | Scott Graham | Scott Graham | DUPLICATE - SEE OH TAB
Internals Site 2 | n/a | Edinburgh MC | Internal (Existing Site) | Edinburgh Mail Centre, 11 Cutltins Road, Edinburgh, EH11 4YY | Scott Forsyth | ross.m.anderson@royalmail.com | S Forsyth emailed 14th Sept to advise that additional frames being installed for Peak. PMc responded 21st Sept noting that our teams are not dealing with frames and whether anything else is required. Awaiting response Priced but returned to Tony F for delivery under Frame moves | AECOM | Derek Penny | Scott Graham | Scott Graham | n/a | n/a | 2021-10-25 | 2023-01-14
Internals Site 3 | n/a | Aberdeen MC | Internal (Existing Site) | Aberdeen Mail Centre Wellington Circle, Aberdeen, AB12 3TT | Scott Forsyth | David.i.noble@royalmail.com | Scoped, price due back 30/9. Programme c.1 week based on last year Aborted 4/10/22 | AECOM | Derek Penny | Scott Graham | Scott Graham | n/a | n/a | 2021-10-25 | 2023-01-14
Internals Site 4 | n/a | DQ Northern Ireland | Internal (Existing Site) | Tomb Street BT1 1AA | Nicky Dunn | andy.p.brady@royalmail.com | Scoping visit carried out 22/09/22. No works required on site as used last Christmas (5th floor in a building already occupied by RMG). | AECOM | Hugh Okne | Scott Graham |  | n/a | n/a | 17/10/2022 | 15/01/2023 | Access arranged for Wednesday 14/09/2022. Draft schedule of works issued ahead of the meeting.
Internals Site 5 | n/a | Gloucester M.C | Internal (Existing Site) | GLMC, Eastern Ave, Gloucester, GL4 3AA | Alan Nicholls | 07872 004928 alan.r.nicholls@royalmail.com | Scoped 26th, issued 27/9 for pricing. PUWER and LOLLER booked in. Sarah to check when doors will be ready for PUWER (currently 20th Oct) Potential variation on bird netting. Meeting on site tomorrow to discuss relocation of cabins and programming. Scoping of ancillary work for Marquee | KKS | Glyn Jones |  |  | n/a | n/a | 2022-11-14 | 2022-12-24 | Contact made with RMG. SEP & PIC regarding access w/c 12/09/22. Works advised as minimal due to area being used last Christmas.
Internals Site 6 | n/a | Exeter MC | Internal (Existing Site) | Exeter Mail Centre, Osprey Road, Sowton Industrial Estate, Exeter, EX2 7XX | Alan Nicholls | 07909 212756 ian.percival@royalmail.com | Covered by Accio works - nothing further for us to do | KKS | Glyn Jones |  |  | n/a | n/a | 2022-11-07 | 2023-01-02
Internals Site 7 | n/a | Exeter MC | Internal (Existing Site) | Exeter Mail Centre, Osprey Road, Sowton Industrial Estate, Exeter, EX2 7XX | Alan Nicholls | 07909 212756 ian.percival@royalmail.com | Covered by Accio works - nothing further for us to do | KKS | Glyn Jones |  |  | n/a | n/a | 2022-11-07 | 2023-01-02
Internals Site 8 | n/a | Chelmsford MC | Internal (Existing Site) | Winsford Way, Springfield, Chelmsford CM2 5AA | Jasmin Mann | Nick Dent nick.j.dent@royalmail.com | Seb to check if there is internal site aswell as marquee with Yvonne. | RLB (South) | Seb Hayter | Yvonne |  | n/a | n/a | 2022-11-07 | 2023-01-27
Internals Site 9 | n/a | South Midlands Plant | Internal (Existing Site) | Royal Mail South Midlands Swan Valley Way | Helen Perry | 07553 367512 mohammad.s.rahman@royalmail.com | Portakabin approved, awaiting delivery date 18/10 - Portakabin need to do a site vist on 20th. Delivery slot TBC | RLB (North) | Andrew Jenkins |  |  | n/a | n/a | 2022-11-24 | 2022-01-20
Internals Site 10 | n/a | Preston MC | Internal (Existing Site) | Preston MC 4 Pitman Way Preston PR11 2BS | Clare Thomson | 07553389287 david.birch@royalmail.com | TRANSFERRED TO MARQUEE | JYM | Mick McKevitt |  |  | n/a | n/a | 2022-10-03 | TBC
Internals Site 11 | n/a | Cardiff MC | Internal (Existing Site) |  | Alan Nicholls |  | Vinci met flooring subcontractor 10/10/22. NO issuses presently 18/10 - on site yesterday, 3 weeks work. | KKS | Glyn Jones |  |  | n/a | n/a | 2022-11-07
Internals Site 12 | n/a | ELDC - Internal Alts | Internal (Existing Site) | Gardeners way, Oliver Road, Grays, RM20 3ED | Tony Foskew |  | PFS instrcuted to attend and complete works before RFS. Paul to confirm Vinci price for lighting etc. PCI sent out. CPP check list sent and signed off. | RLB | Seb Hathaway | Yvonne Duong |  | n/a | n/a | 2022-10-31 | 2023-01-31
Internals Site 13 |  | Glasgow | Internal (Existing Site) | Prestwick Airport , Transit House | Scott Forsyth | mark.docherty@royalmail.com | Prestart held, SoS 19/10, additional steelwork instructed. PUWER 1st November, Scissor lift now requires testing as it is being brought in from Edinburgh | AECOM | Scott Graham | Derek Penny | Scott Graham |  |  | 2022-11-07 | 2023-01-14 | Contact made with RMG. SEP & PIC regarding access w/c 12/09/22. Works advised as minimal due to area being used last Christmas.
Internals Site 14 | n/a | Atherstone HUB | Internal (Existing Site) | Atherstone HUB, Riversdale Road, Atherstone, CV9 1FA | Helen Perry | 07553383888 balbinder.harar@royalmail.com | Internal line marking required for the IA works. Separate PO raised, waiting for start. Works being undertaken 3rd Oct. Line marking complete 4/10/22, | RLB (North) | Andrew Jenkins |  |  | n/a | n/a | n/a | n/a
Internals Site 15 | n/a | Atherstone HUB | Internal (Existing Site) | Atherstone HUB, Riversdale Road, Atherstone, CV9 1FA | Helen Perry | 07553383888 balbinder.harar@royalmail.com | Portakabin being priced up, query over power to unit. Fencing requirements de-scoped, specifying and pricing underway | RLB (North) | Andrew Jenkins |  |  | n/a | n/a | Portakabin - 31st Oct Fencing - assumed 31st but gate may need to be fabricated | n/a
Internals Site 16 |  | ELDC - Yard Line Marking | Internal (Existing Site) | Gardeners way, Oliver Road, Grays, RM20 3ED | Tony Foskew |  | Linemarking to be included within other ELDC works. |  | Seb Hathaway | Yvonne Duong |  |  |  | 2022-10-31 | n/a
Note on B4: Paul McGouran: Applies to OH, Parking, VOC sites
Note on C5: Paul McGouran: Might be a temp unit / Outhouse - confirm with SEP
Note on O9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Amended 18/10, following discussion with SP
Note on O13: Paul McGouran: Amended in line with HP instruction to AJ
Note on O16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Amended following site scoping visit (previous date was an error - referred to 2021)

## Xmas - Marquees
ROYAL MAIL XMAS 22 - TEMPLATE | [15 empty] | Updated 12th September
REFS |  | DETAILS | [5 empty] | SURVEYOR |  |  |  | STATUS |  |  |  | OTHER
SEP REF | L CATON REF | SITE | Type | ADDRESS | Special Events Planner | Site Contact | Comments | PRACTICE | SURVEYOR 1 | SURVEYOR 2 | Previous Surveyor | LEASE START | LEASE EXPIRY | RFS | LDS | COMMENTS
Marquee 1 | n/a | South Midlands Plant | Marquee | Royal Mail South Midlands Swan Valley Way NORTHAMPTON NN4 9DR | Helen Perry | 07553 367512 mohammad.s.rahman@royalmail.com> | No longer required. Confirmed by Helen on 21/09/22 | RLB | Matt Hayter |  |  |  |  | 2022-11-21 | 2023-01-13 | Repeat of 2021
Marquee 2 | n/a | Buckingham DO | Marquee | Buckingham DO Market Hill BUCKINGHAM MK18 1AA | Helen Perry | 01280 744901 Paul Murray paul.c.murray@royalmail.com | Accio plans returned. FRA, Chubb, Building Control contacted PCI sent to RLB PD | RLB | Seb Hathaway | Bushra Ahmed |  |  |  | 2022-11-07 | 2023-01-14 | Repeat of 2021 | Assuming last years still stands
Marquee 3 | n/a | Birmingham Plant | Marquee | Birmingham Mail Centre St Stephens Stree BIRMINGHAM B6 4AA | Helen Perry | elliot.geddes@royalmail.com / corey.kitchen@royalmail.com 07436 547081 / 07801 094132 |  | RLB | Matt Hayter |  |  |  |  | 2022-11-07 | 2023-01-14 | Repeat of 2021
Marquee 4 | n/a | Nottingham Plant | Marquee | Nottingham Mail Centre Padge Road Beeston NOTTINGHAM NG9 2RR | Helen Perry | mark.richardson@royalmail.com jennifer.e.taylor@royalmail.com 07736 363572 / 07411 172679 |  | RLB | Matt Hayter |  |  |  |  | 07/11/2022 - TBC | 14/01/2023 - TBC | Repeat of 2021
Marquee 5 | n/a | Carlisle Plant | Marquee | Royal Mail Junction Street Carlisle CA1 1AA | Clare Thomson | 07483373539 derek.copland@royalmail.com |  | JYM | Matt Kerr |  |  |  |  | 2022-10-17 | 2023-01-09 | Repeat of 2021
Marquee 6 | n/a | Chester MC | Marquee | Chester Mail Centre Jupiter Drive Chester CH70 8DF | Clare Thomson | sailesh.maisuria@royalmail.com |  | JYM | Matt Kerr |  |  |  |  | 2022-10-17 | 2023-01-09 | Repeat of 2021 but slightly alterered
Marquee 7 | n/a | Manchester MC | Marquee | Manchester MC, Oldham Rd, Manchester, M4 5AA | Clare Thomson | 07921 866228 lee.kemp@royalmail.com |  | JYM | Stuart Baird |  |  |  |  | 2022-10-17 | 2023-01-09 | Repeat of 2021
Marquee 8 | n/a | Inverness MC | Marquee | 7 Strothers Lane, Inverness, IV1 1AA | Scott Forsyth | allen.skinner@royalmail.com |  | AECOM | Derek Penny | Scott Graham | Scott Graham |  |  | 2022-11-01 | 2023-01-06 | New site for 2022
Marquee 9 | n/a | Swindon MC | Marquee | RM Swindon MC, Rowland Hill Close, Dorcan, Swindon SN3 5TQ | Andy Martin | 07436 288167 phlip.gee@royalmail.com |  | KKS | Glyn Jones |  |  |  |  | 7th November 2022 | 16th Jan 2023 | Repeat of 2021
Marquee 10 | n/a | Swindon MC | Marquee | RM Swindon MC, Rowland Hill Close, Dorcan, Swindon SN3 5TQ | Andy Martin | 07436 288167 phlip.gee@royalmail.com |  | KKS | Glyn Jones |  |  |  |  | 7th November 2022 | 16th Jan 2023 | Repeat of 2021
Marquee 11 | n/a | Swindon MC | Marquee | RM Swindon MC, Rowland Hill Close, Dorcan, Swindon SN3 5TQ | Andy Martin | 07436 288167 phlip.gee@royalmail.com |  | KKS | Glyn Jones |  |  |  |  | 7th November 2022 | 16th Jan 2023 | Repeat of 2021
Marquee 12 | n/a | Southampton MC | Marquee | Southampton Mail Centre Mitchell Way, Southampton SO18 2XX | Andy Martin | 07483 353489 daniel.v.jones@royalmail.com |  | KKS | Glyn Jones |  |  |  |  | 17/10/2022 | 14/01/2023 | Repeat of 2021
Marquee 13 | n/a | NDC VOC | Marquee | National Distribution Centre Danes Way DIRFT East Northampton NN6 7DD | Nicky Dunn | 07553381777 & 07776 990091 james.h.parker@royalmail.com & Paolo.fiorello@royalmail.com |  | RLB | Matt Hayter |  |  |  |  | 2022-10-01 | 2023-02-01 | Repeat of 2021
Marquee 14 | n/a | Croydon MC | Marquee | Croydon Mail Centre Beddington Farm Road Croydon CR9 4AA | Nicole Menon | james.doyle@royalmail.com | Accio plans returned. FRA, Chubb, Building Control contacted PCI sent to RLB PD | RLB | Seb Hathaway | Bushra Ahmed |  |  |  | 2022-10-27 | 2023-01-21 | Same site and location but ongoing works by Vinci on site may adjust position / layout slightly. Need to liaise with Vinci as will be working under their F10
Marquee 15 | n/a | Jubilee Mail Centre | Marquee | Jubilee Mail Centre Godfrey Way Hounslow TW4 5XX | Nicole Menon | 07885 875272 - eric.ashiagbor@royalmail.com | Plans not finalised. One marquee now (larger). PCI to be issued to RLB PD. | RLB | Seb Hathaway | Bushra Ahmed |  |  |  | 2022-10-31 | 2023-01-27 | Same site but options being reviewed. Likely there are two marquees here.
Marquee 16 | n/a | Dorset Mail Centre | Marquee | Nuffield Industrial Estate, Poole, Dorset, BH17 0AA | Alan Nicholls | 07841 785511 thomas.wilkinson@royalmail.com |  | KKS | Glyn Jones |  |  |  |  | 2022-11-07 | 2023-01-07 | Repeat of 2021
Marquee 17 | n/a | Bristol South DO | Marquee | Kent Street Bristol BS3 3NR | Alan Nicholls | 07872 004928 alan.r.nicholls@royalmail.com | MAY BE ABORTED - CHECK WITH ALAN NICHOLLS | KKS | Glyn Jones |  |  |  |  | 2022-11-07 | 2023-01-30
Marquee 18 | n/a | Winterbourne DO | Marquee | 22 Bristol Road Winterbourne Bristol BS36 1RG | Alan Nicholls | 07872 004928 alan.r.nicholls@royalmail.com |  | KKS | Glyn Jones |  |  |  |  | 2022-11-15 | 2023-01-03 | Already on site
Marquee 19 | n/a | Exeter MC | Marquee | Exeter Mail Centre, Osprey Road, Sowton Industrial Estate, Exeter, EX2 7XX | Alan Nicholls | 07909 212756 ian.percival@royalmail.com |  | KKS | Glyn Jones |  |  |  |  | 2022-10-31 | 2023-01-08 | Repeat of 2021
Marquee 20 | n/a | Truro MC | Marquee | Truro Mail Centre, Newham Road, Truro TR1 1AA | Alan Nicholls | 07736 786891 glyn.ford@royalmail.com |  | KKS | Glyn Jones |  |  |  |  | 2022-11-14 | 2022-12-24 | Repeat of 2021
Marquee 21 | n/a | Swansea MC | Marquee | Siemens Way, Swansea, SA1 1AA | Alan Nicholls | 07872 004928 alan.r.nicholls@royalmail.com |  | KKS | Glyn Jones |  |  |  |  | 2022-11-07 | 2022-01-02 | Repeat of 2021
Marquee 22 | n/a | Havefrordwest DO | Marquee | Merlins Bridge Haverfordwest SA61 1XT | Alan Nicholls | 07872 004928 alan.r.nicholls@royalmail.com |  | KKS | Glyn Jones |  |  |  |  | 2022-11-07 | 2023-01-29 | Repeat of 2021
Marquee 23 | n/a | Congleton DO | Marquee | Unit 9 Greenfield Farm Industrial Estate, CONGLETON, CW12 4ZZ | Clare Thomson | david.main@royalmail.com 07595 610883 |  | JYM | Stuart Baird |  |  |  |  | 14th November 2022 | 24th December 2022 | New Site for 2022
Marquee 24 | n/a | Romford MC | Marquee | Romford Mail Centre Queen Elizabeth House Sandgate Close ROMFORD RM7 0AB | Jasmin Mann | Rashid Choudry rashid.choudry@royalmail.com | PCI, FRA, CHUBB Building Control and PAP all issued. CPP to be returned by Accio. | RLB | Seb Hathaway | Yvonne Duong |  |  |  | 2022-10-31 | 2023-01-20 | RM to confirm - works on site by Vinci may impede position and layout
Marquee 25 | n/a | Peterborough MC | Marquee | Papyrus Road, Peterborough, PE4 5PE | Jasmin Mann | sarah.j.oshaughnessy@royalmail.com |  | RLB | Matt Hayter |  |  |  |  | 2022-10-24 | 2023-01-13 | Repeat of 2021
Internals Site 10 Marquee 26 | n/a | Preston MC | Internal (Existing Site) | Preston MC 4 Pitman Way Preston PR11 2BS | Clare Thomson | 07553389287 david.birch@royalmail.com | TRANSFERRED FROM MARQUEE - CANCELLED | JYM | Mick McKevitt |  |  | n/a | n/a | 2022-10-03 | TBC
Marquee 27 |  | Glasgow | Marquee | Glasgow MC, 20 Turner Road, Glasgow, G21 1AA | Scott Forsyth | TBC | AECOM received Accio proposal for new marquee. RMG to confirm the proposal is acceptable. AECOM have carried out site inspection and will progress PCI, PAP, SOW etc which will be issued early this week. | AECOM | Stephen Pope | Derek Penny |  |  |  | 2022-11-07 | 2023-01-14 | Repeat of 2021 | AECOM waiting for tasking order £1540 email to Paul 10/10 FRA
Marquee 28 |  | Northampton | Marquee | waiting response from stephen casey 06/09 | Helen Perry | to find out |  | RLB | Seb Hathaway |  |  |  |  | 2022-10-01 | 2023-02-04 | Assume this is the same as Marquee 13
Marquee 29 |  | Newport East | Marquee | Unit 12 - 13 Estuary Road, Newport; NP19 4AA | Alan Nicholls | Aborted 11/10/22 | checking with SEP - Accio noted 9th Sept |  | Glyn Jones |  |  |  |  | 2022-11-07 | 2023-01-21 | Previously installed in 2021 peak - Alan Nichols confirmed requirement for 2022 to Steve Casey
Marquee 30 |  | Chelmsford Floor | Marquee | Windsford Way, Chelmsford CM2 5AA | Jasmin Mann |  | PCI, FRA, CHUBB Building Control and PAP all issued. CPP to be returned by Accio. | RLB | Seb Hathaway | Yvonne Duong |  |  |  | 2022-11-07 | 2023-01-27 | RFS Date confirmed on 13th Sept | Updated RB, he's now sent to Praxis to quote for FRA
Marquee 31 |  | Norwich MC | Marquee | 13-17 Thorpe Road, Norwich NR1 1AA | Jasmin Mann |  | Likely to be removed from programme to be replaced with Outhouse. PCI to be issued to RLB PD. | RLB | Seb Hathaway | Bushra Ahmed |  |  |  | 07/11/2022 (Accio believe 11/11/2022) | 2022-12-31
Marquee 32 |  | Bude DO | Marquee |  | Alan Nicholls |  | Added 23rd September | KKS | Glyn Jones |  |  |  |  | 2022-11-07 | 2023-01-28 | Repeat of 2021
Marquee 33 |  | Sheffield South DO | Marquee |  | Anne Oconnor |  | Added 26th September. General enquiry sent to Accio direct, awiting information before they can price and programme | RLB | Matt Hayter |  |  |  |  | TBC | TBC
Marquee 34 |  | Edinburgh MC | Marquee | Edinburgh MC | Scott Forsyth | TBC | AECOM received Accio proposal for new marquee. RMG to confirm to proceed. AECOM to site visit to see if additional works required and will progress PCI, PAP, SOW etc which will be issued as soon as possible. RMG to confirm RFS date. | AECOM | Derek Penny | Scott Graham | [5 empty] | Repeat of 2022 Marquee
Marquee 35 |  | Gloucester MC | Marquee |  |  |  | Accio raised on 7th October that they’ve been asked to scope one at the MC. Made them aware that we are planning other works on site | [9 empty] | Updated RB, he's now sent to Praxis to quote for FRA
Marquee 36 |  | Greenford MC | Marquee
Marquee 37 |  | HWDC MC | Marquee
Note on B4: Paul McGouran: Applies to OH, Parking, VOC sites
Note on C5: Paul McGouran: Might be a temp unit / Outhouse - confirm with SEP
Note on O11: Paul McGouran: Check - Accio priced for 25th Oct to 28th Jan
Note on O18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Amended 13/9/22 - S casey email to N Menon
Note on O19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Seb Hathaway email of 6th Sept Reply: Nicole emailed 13th Sept to bring this forward Reply: Confirmed it is the 31st October by Nicole on 26/9
Note on O23: Paul McGouran: Revised 15/9/22
Note on O33: Paul McGouran: Assumed, from Accio end date

## Xmas - ParkingVOC
ROYAL MAIL XMAS 22 - TEMPLATE
REFS |  | DETAILS | [5 empty] | SURVEYOR |  |  |  | STATUS
SEP REF | L CATON REF | SITE | Type | ADDRESS | Special Events Planner | Site Contact | Comments | PRACTICE | SURVEYOR 1 | SURVEYOR 2 | Previous Surveyor | LEASE START | LEASE EXPIRY | RFS | LDS
Site 1 |  | Rugeley DO | Parking |  | Helen Perry | 07746 294582 richard.p.knight@royalmail.com | Likely no works required - to confirm with SEP | RLB | Matt Hayter |  |  |  |  | 2022-11-07 | 2023-01-14
Site 2 | 23 | Coventry VOC | VOC | Secland Group, Bedworth Road, CV6 6JR | Helen Perry | 07553 379191 Ricki.ravat@royalmail.com | On site 19th to complete | RLB | Andrew Jenkins |  |  | 2022-10-01 |  | 2022-10-01 | 2023-02-01
Site 3 |  | Atherstone VOC | O Licence Only |  | Helen Perry | 07423524136 dean.harris@royalmail.com |  | RLB | Matt Hayter |  |  |  |  | N/A | N/A
Site 4 | 3 | Northern Ireland MC VOC | VOC | Antrim Road Site - Ballycraigy Business Park, 655 Antrim Road, Mallusk, BT36 4RG | Nicky Dunn | james.ferguson@royalmail.com 07553375334 | SITE MAY CHANGE | AECOM | Hugh Okane | Stephen Pope
Site 5 | 4 | Southampton MC | Parking | Southampton Intl Airport Ltd Southampton, Hampshire | Andy Martin | 07483 353489 daniel.v.jones@royalmail.com | Likely no works required - to confirm with SEP | KKS | Glyn Jones |  |  |  |  | 31/10/2022 | 23/12/2022
Site 6 | 35 | Croydon MC | Parking | Ikea Croydon | Nicole Menon | james.doyle@royalmail.com | No works required | RLB | Seb Hathaway |  |  |  |  | 2021-07-11 | 21/01/2022
Site 7 | 36 | Exeter MC | Parking | B&Q at Avocet Road Exeter EX2 7JF | Alan Nicholls | 07909 212756 ian.percival@royalmail.com | Likely no works required - to confirm with SEP | KKS | Glyn Jones |  |  |  |  | 2022-11-01 | 2022-12-24
Site 8 | 37 | Swansea MC | Parking | Mercure Swansea Hotel, Phoenix Way, Llansamlet, Swansea SA7 9EG | Alan Nicholls | 07872 004928 alan.r.nicholls@royalmail.com | Likely no works required - to confirm with SEP | KKS | Glyn Jones |  |  |  |  | 2022-11-14 | 2022-12-24
Site 9 | 39 | Carlisle Plant | Parking | Newsquest site | Clare Thomson | 07483373539 derek.copland@royalmail.com | No works required | JYM | Stuart Baird |  |  |  |  | 2022-10-03 | 2023-01-08
n/a | 42 | Peterborough MC | Parking | Papyrus Road, Peterborough, PE4 5PE | Jasmin Mann | sarah.j.oshaughnessy@royalmail.com | Likely no works required - to confirm with SEP | RLB | Andrew Jenkins |  |  |  |  | 2022-11-28 | 2022-12-24
| 30 | NHC VOC - ABORTED |  |  | Jasmin Mann | 07483 419190 stephen.conquest@royalmail.com | [7 empty] | 2022-10-23 | 2023-01-14
Site 12 | 40 | Louth D.O | Parking | TBC | Anne O'Connor | aaron.mcghie@royalmail.com 07483382350 | No works required | RLB | Seb Hathaway |  |  |  |  | NA | NA
Site 13 | 25 | SDC | VOC | New Street, Newmains, ML2 | Scott Forsyth | 07483354160. daniel.wood@royalmail.com | Prestart w/c 24th and works will be complete in a week. | AECOM | Derek Penny | Scott Graham |  | Complete |  | 2022-10-01 | 2023-01-31
Site 14 |  | ELDC | VOC | Gardeners way, Oliver Road, Grays, RM20 3ED | Tony Fostekew | Dean Claydon '07841 785927 | No works required | RLB | Seb Hathaway |  |  | n/a - site live |  | 2022-10-31 | 2023-01-31
Site 15 | 2 | SDC Edinburgh | VOC | Royal Highland Centre, Ingliston, Newbridge EH28 8NB | Scott Forsyth | 07483354160. daniel.wood@royalmail.com | No works required | AECOM | Derek Penny |  |  |  |  | 2021-10-01 | 2022-01-31
Site 16 | 32 | NEDC VOC | VOC |  | Anne O'Connor | 07776990091 & paolo.fiorello@royalmail.com | May end up sharing with Tyneside | RLB | Matt Hayter |  |  |  |  | 2021-10-01 | 2022-01-31
Site 17 | 21 | PRDC VOC | VOC |  | Tony Fostekew | Rick Archer 07801 093728 | Neil Dangolitis email 21st Sept to Seb Hathaway - no site for PRDC this year | RLB | Seb Hathaway |  |  |  |  | 2021-11-15 | 2022-01-31
Site 18 | 19 | SWDC VOC | VOC | Plot 58 Severnbanks, Central Avenue, Bristol, BS10 7SD | Alan Nicholls | Mark Charlton / Pete Hicks 0772 5829586 | LRA undertaken today, cabins on site as well as lighting. Bins - chase date | KKS | Sarah Palmer |  |  | 2022-09-19 |  | 2022-10-24 | 2022-01-27
Site 18 | 19 | HWDC | VOC | Unit 1, Orchard Herb Farm, Lake End Road, , SL4 6QS | Alan Nicholls | Mark Charlton / Pete Hicks 0772 5829586 | SITE MAY CHANGE | KKS | Sarah Palmer |  |  |  |  | 2022-10-24 | 2022-01-27
n/a | 34 | Glasgow PAR | Parking | Alpha Car Park, Prestwick Airport | Scott Forsyth | scott.forsyth@royalmail.com/ '07725447935 | No works required | AECOM | Stephen Pope |  |  |  |  | 2022-11-07 | 2022-01-31
n/a | 41 | NDC PAR | Parking | Ingram Micro UK (Ltd), Parklands, DIRFT East, Crick | Nicky Dunn | chris.m.brown@royalmail.com / 07483 419 195 | Likely no works required - to confirm with SEP | RLB | Andrew Jenkins |  |  |  |  | 2022-10-24 | 2023-01-29
Site 20 |  | Skelton Grange | VOC | Skelton Grange Road, Leeds
Note on B4: Paul McGouran: Applies to OH, Parking, VOC sites
Note on C5: Paul McGouran: Might be a temp unit / Outhouse - confirm with SEP
Note on O18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Amended following site scoping visit (previous date was an error - referred to 2021)
Note on O22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Amended 28th August

## PFW Xmas
ROYAL MAIL XMAS 22 - OUTHOUSES
REFS |  | DETAILS | [5 empty] | SURVEYOR |  |  |  | STATUS
SEP REF | L CATON REF | SITE | Type | ADDRESS | Special Events Planner | Site Contact | Comments | PRACTICE | SURVEYOR 1 | SURVEYOR 2 | Previous Surveyor | LEASE START | LEASE EXPIRY | RFS | LDS
PFW 1 |  | Atherstone HUB | Existing Royal Mail Site | Atherstone HUB, Riversdale Road, Atherstone, CV9 1FA | Barry Gordon | 07553383888 balbinder.harar@royalmail.com | Costs approved, power down planned in. Prestart to be arranged | RLB | Andrew Jenkins |  |  | N/A | N/A | 2022-11-07 | TBC
Note on B4: Paul McGouran: Applies to OH, Parking, VOC sites
Note on C5: Paul McGouran: Might be a temp unit / Outhouse - confirm with SEP

## Template
ROYAL MAIL XMAS 22 - TEMPLATE
REFS |  | DETAILS | [5 empty] | SURVEYOR |  |  |  | STATUS |  |  |  | SCHEDULE OF CONDITION |  | SCOPE OF WORKS | [5 empty] | HEALTH & SAFETY |  |  |  | FINANCES | [8 empty] | PROGRAMME |  |  |  | SITE - KEY DATES OF ATTENDANCE |  |  |  | OTHER
[28 empty] | WORKS |  |  |  | FEES
SEP REF | L CATON REF | SITE | Type | ADDRESS | Special Events Planner | Site Contact | Comments | PRACTICE | SURVEYOR 1 | SURVEYOR 2 | Previous Surveyor | LEASE START | LEASE EXPIRY | RFS | LDS | INSPECTION | ISSUED | INSPECTION | ISSUED | SCOPE APPROVED BY RM | PRICE RETURNED | RM APPROVED | INSTRUCTED | ASBESTOS SURVEY | ASBESTOS R&D | PCI | CPP REVIEWED | VINCI | ACCIO | CHUBB | OTHER | PAP | L8 LRA | PUWER | FRA | OTHER | COMMENCEMENT ON SITE | HANDOVER DATE | DILAPS START | DILAPS END | CHUBB | L8 RISK ASSESSMENT | SITE LOG BOOK | FIRE RISK ASSESSMENT | COMMENTS
Note on B4: Paul McGouran: Applies to OH, Parking, VOC sites
Note on C5: Paul McGouran: Might be a temp unit / Outhouse - confirm with SEP
Note on AF4: Paul McGouran: Add details as a comment
Note on AK4: Paul McGouran: Add details as a comment
Note on AL4: Paul McGouran: Add planned start if not commenced
Note on AM4: Paul McGouran: Add planned date if not complete