## Outhouses
ROYAL MAIL XMAS 23/24 - OUTHOUSES
REFS | DETAILS | [5 empty] | SURVEYOR |  |  |  | STATUS |  |  |  | OTHER
SEP REF | SITE | Type | ADDRESS | Special Events Planner | Site Contact | Comments | PRACTICE | SURVEYOR 1 | SURVEYOR 2 | Previous Surveyor | LEASE START | LEASE EXPIRY | RFS | LDS | COMMENTS
Site 1 | Bristol MC | Outhouse | TBC | Alan Nicholls | 07802 928683 robert.j.paterson@royalmail.com | 4/9/23 - Centre Seven aborted due to cost. 11/9/23 - RM discussing internally 19/9 - going to Llanishen | KKS | Glyn Jones |  |  |  |  | 2023-10-31 | 2024-01-28 | Inspected, works required to improve lighting - £50k allowed provisionally, otherwise OK - lots of racking for tenant to remove. Also want us to take building for 6 months so is expensive.
Site 3 | South East PSC | Outhouse | Tetris Rockware Avenue Greenford UB6 0AD | Andrew Martin | furat.muhi-al-din@royalmail.com 07841 466245 | 29/8 - need to revisit in a couple of weeks once it is clearer whether the building will be used. 11/9/23 - still in discussion (with Bristol) but likely no work 26/9 - Robbie to check with A Martin that there is definatley no work to undertake 3/10 - to do 17/10 - VOC being used, BP45 underway | RLB | Robbie Brindley |  |  | Ongoing |  | 2023-11-06 | 1st week in Jan, then decommission - 14th Jan
Site 4 | Manton | Outhouse | Unit 4 Manton Wood Retford Road Manton Wood Enterprise Park Worksop S80 2RS | Anne O'Connor | Ian.J.Brown@royalmail.com 07802791840 | 4.9.23 - SOW issued for pricing 11/9/23 - Anne O reviewing costs/scope 19/9 - approved but need to review cleaning items (so that element TBC) 26/9 - cleaning now going to PFSL, Trios instructed on remainder. PO now received. Awaiting start date. 3/10 - AJ to confirm 17/10 - Works due to complete today, LRA and gas safety cert awaited 24/10 - fit out complete, awaiting SMS legionella this week. Gas safety due ASAP | RLB | Andrew Jenkins |  |  | Ongoing |  | RFS by end of Oct 2023 | 2024-01-08 | Small elements of work to undertake - AJ has questions over transporting of goods which were removed from site - AJ liaising with Anne Oconnor
Site 5 | Tyneside OH | Outhouse |  | Anne O'Connor | 07889929494 philip.welsh@royalmail.com |  | RLB | Andrew Jenkins |  |  |  |  | 2023-10-30 | 2024-01-08
Site 6 | South Midlands Plant | Outhouse | Royal Mail Northampton PSC Unit 5 Panattoni Park Weedon Road NORTHAMPTON NN7 4DE *Same space needed as for 2022* | Helen Perry | mohammad.s.rahman@royalmail.com 07553 367512 | HP confimed Askona will be moving frames, no other works. | RLB | Andrew Jenkins |  |  | Ongoing |  | 2023-10-09 | 2024-01-20 | HP confimed Askona will be moving frames, no other works
Site 7 | East of Scotland Outhouse | Outhouse | Royal Highland | Scott Forsyth | 07736 786332 david.condon@royalmail.com | 4.9.23 - still unable to find a site, alternatives being looked in to. 11/9/23 - no change 18/9 - potential reach out to Royal Highland again 26/9 - site visit being undertaken at RHS today, await feedback 3/10 - costs awaited. L Garner has approved costs based on last year (£190k), Trios price awaited, compliance docs from LL awaited POST MEETING NOTE: Awaiting LL to agree to SoW, some works to be passed to LL but needs their agreement. Unlikely 9th Oct will be achieved, TBC. 17/10 - in progress, works to commence 24th Nov to 27th Nov. 24/10 - Electricians cost from RHS required ASAP. Scott chasing. IT visiting this Wednesday, 31/10 Awaiting on Electrician costs and info on hire equipment | AECOM | Derek Penny | Abi Akinyemi | Derek Penny | 24/11/23 | 28/1/24 | 2023-11-07 | 2024-01-14 | Various sites inspected on 10/08/23. Other sites to be visited on 23rd Aug 23. Await RMG confirming which site we are to use.
Site 8 | Prestwick Outhouse | Outhouse | Prestwick Airport, Transit House, KA9 2QA | Scott Forsyth | graeme.turnbull@roiyalmail.com 07568 564429 | Costs rec'd - needs discussion with PFSL re maintenance. 11/9/23 - can we review scope again to check we are doing the minimum 14/9/23 - approved to proceed 26/9 - PO received, await start date, Trios CPP. 3/10 - starting 9th Oct. DP to advise LL so security can be disengaged 17/10 - due to be complete this week. Dock leveller issue to be resolved with Iain Muir, IT install due next week. 31/10 Complete. Issue with boiler being repaired 2/11 | AECOM | Derek Penny | Abi Akinyemi | Scott Graham | Ongoing |  | 2023-11-07 | 2024-01-14 | Costs received from TRIOS. Currently reviewing and waiting on confirmation to proceed. Meeting on Site Thursday to agree scope for heating and cabins - this will tidy up costs. RLB to confirm PFSL requirements for lighting,
Site 9 | Norwich MC Outhouse | Outhouse | Former Tuffnells Depot, 23 Vulcan Rd S, Norwich NR6 6AG | Nicky Dunn | 07841568085 angela.travis@royalmail.com | Inspected, RM H&S team revisiting on 7.9.23 - Vulcan Road vs. Diamond Road 11/9/23 - discussion on 12th to agree preferred site - 12/9 - Vulcan Road selected, full scoping visit with contractor required 19/9 - site visit on 20th to scope. 26/9 - scoped, awaiting costs back from Vinci. 3/10 - as above. FRA request to be submitted. Michael to check on PUWER also. POST MEETING NOTE - aiming to complete the aquisition around 24th Oct. Schedule of condition required. 17/10 - Green light to proceed has been given and vinci mobilising for the 24th. 24/10 - potentially starting on 30th, Robbie to update. | RLB | Robbie Brindley |  |  | 2023-10-24 |  | 2023-11-14 | 2023-12-31

## Internals
ROYAL MAIL XMAS 23/24 - INTERNALS
REFS | DETAILS | [5 empty] | SURVEYOR |  |  |  | STATUS |  |  |  | OTHER
SEP REF | SITE | Type | ADDRESS | Special Events Planner | Site Contact | Comments | PRACTICE | SURVEYOR 1 | SURVEYOR 2 | Previous Surveyor | LEASE START | LEASE EXPIRY | RFS | LDS | COMMENTS
Site 1 | Cardiff MC | Internals | Cardiff Mail Centre, 220-228 Penarth Road, Cardiff, CF11 8TA | Alan Nicholls | 07850 815888 andrew.colclough@royalmail.com | To get the mezzanine area into a condition that is suitable to use for Peak 2023. Awaiting dates from SEP to attend. 5/9/23 - costs rec'd - query over the SoW that has been priced. Glyn comments - temp heating costs seem low. Question over scope in terms of draught strips - RM to confirm 11/9/23 - remove draught strips from scope,awaiting revised scope costed 19/9- approved to proceed 26/9 - Vinci PO imminent, awaiting start date 3/10 - start 13th Nov. LARC booked in to remove sink pad. 17/10 - Vinci mobilising ready for 13th November, c.1 week work. Vinci will be requested to provide costs for permanent heating. 24/10 - no change, awaiting start 31/11 Starts 13th with LARC in attendance | KKS |  |  |  | n/a | n/a | 2023-11-27 | 2023-12-24 | Heating removed from vacant floor area, proposal requested from Vinci for reinstating. | XXX
Site 2 | Exeter MC | Internals | Exeter Mail Centre, Osprey Road, Sowton Industrial Estate, Exeter, EX2 7XX | Alan Nicholls | 07909 212756 ian.percival@royalmail.com | Harris Fencing to create safe walkway between MC and Marquee #1 & WBC as per Christmas 2022. The supporting feet for the Heras fencing need to be the red and white retangular type as per 2022. There also needs to be good quality warning lights on the Heras fencing to alert drivers. This needs to be in place the same time the Marquee is ready. Total approximately 100 metre in length | KKS |  |  |  | n/a | n/a | 2023-11-06 | 2023-12-31
Site 3 | Exeter MC | Internals | Exeter Mail Centre, Osprey Road, Sowton Industrial Estate, Exeter, EX2 7XX | Alan Nicholls | 07909 212756 ian.percival@royalmail.com | Two sets of temporary traffic lights for the official yard. This needs to be in place the same time the Marquee is ready | KKS |  |  |  | n/a | n/a | 2023-11-06 | 2023-12-31
Site 4 | Gloucester M.C | Internals | Gloucester Mail Centre, Eastern Ave, Gloucester, GL4 3AA | Alan Nicholls | 07872 004928 alan.r.nicholls@royalmail.com | Portacabin 1 x messing & 1 x toilet block Male and Female. Awaiting if Bristol Outhouse to see if it commences. Meeting Friday 8th for scoping visit 11/9/23 - scoped, to issue to RM for approval 19/9 - KKS to issue Scope of Works to Vinci 26/9 - awaiting costs back from Vinci 3/10/23 - costs to be chased. Looking to start in 2 weeks. 17/10 - Vinci mobilising, awaiting CPP. 24/10 - CPP promised today, starting as soon as signed off. 31/11 Ready for service this week. Awaiting H&S docs from PC | KKS |  |  |  | n/a | n/a | 2023-11-06 | 2023-12-24 | May not be required if Bristol OH procured
Site 5 | South Wales / West PSC | Internals | South West PSC, Ty-Glas, Llanishen, Cardiff, CF14 5DU | Alan Nicholls | 07872 004928 alan.r.nicholls@royalmail.com | To get the PSC into a condition that is suitable to use for Peak 2023. Awaiting dates from SEP to attend. 5/9/23 - costs rec'd, to review. Glyn comments - testing and commissioning items - PFSL scope? 11/9/23 - RM still considering this site alongside Bristol etc 19/9 - aproved to proceed but asked that Alan Nicholls double checks scope 26/9 - awaiting start date. PMc will chase Alan N re scope - post meeting note, AN happy with scope 3/10/23 - proposed start 6th November, additional site visit on Friday to discuss additional scope. 17/10 - revised scope meeting on 16th to accommodate Bristol OH. Some additional WC's required (2 male & female), additional site clearance required. RFS date brought forward to 6th Nov - working alongside Vinci 24/10 - Biffa bins gone, cabins due this week. Scisor lifts from Tetris this Friday and then Dawson rental the following week. 31/11 On site. Working to RFS 6/11. Minor variations recieved. Awaiting costs for toilets from Vinci | KKS |  |  |  | n/a | n/a | 2023-11-06 | 2023-12-24 | Scissor lift query - existing lifts need servicing, and potentially some new ones being hired in. Needs response from Alan | XXX
Site 6 | South Midlands Plant | Internals | Royal Mail South Midlands Swan Valley Way NORTHAMPTON NN4 9DR | Helen Perry | mohammad.s.rahman@royalmail.com 07553 367512 | Portacabin 6m x 5m = 30sqm - same as provided for 2022. Items sent out to pricing for Trios. 5/9/23 - costs rec'd and reviewed, need RM approval 11/9/23 - Andy Martin checking on whether this is needed 19/9 - Andy visiting site on 21st Sept. Approved to proceed if he confirms they need it. | RLB | Andrew Jenkins |  |  | n/a | n/a | 2023-11-20 | 2023-12-24
Site 7 | Chelmsford MC Internal | Internals | Winsford Way, Springfield, Chelmsford CM2 5AA | Nicky Dunn | nick.j.dent@royalmail.com | Temporary Floor Same as last year. Awaiting new dates from Nicky Dunn. MARQUEE SCHEME | RLB | Seb Hathaway |  |  | n/a | n/a | 30/10 for floating floor 20/11 frames operational | 2024-01-14
Site 8 | DQ Northern Ireland Internal | Internals | Tomb Street BT1 1AA | Nicky Dunn | mark.magee@royalmail.com 07553388341 | Support NIMC with overflow and space to complete operational requirements - survey required. NO WORKS REQUIRED | AECOM | Hugh O'Kane |  |  | n/a | n/a | 13/11/2023 | 29/03/2024 | Scoping visit carried out this morning, same area as last year on the fifth floor and requires no works.
Site 9 | Aberdeen MC Basement | Internals | Aberdeen Mail Centre, Wellington Circle, Aberdeen, AB12 3TT | Scott Forsyth | david.i.noble@royalmail.com 07436 033191 | Internal works to return basement to operational area, Electrics and dock leveller need testing. (In 2021/22 this testing was carried out locally by RMPFS). 5/9/23 - costs due back this week 14/9/23 - costs returned and reviewed. Awaiting RM approval 19/9 - approved to proceed 26/9 - awaiting start date from PFSL 3/10/23 - PFSL chased for start date. 17/10 - training dates being arranged. completion date tbc. 24/10 - awaiting SF to confirm dates for training. 31/11 Works ongoing. Awaiting a reduced scope training for scissor lift from Briggs | AECOM | Derek Penny | Abi Akinyemi | N/A | n/a | n/a | 2023-11-07 | 2024-01-20 | RMG have approved costs. LOLER inspections with RMG/Briggs - RMG to confirm numbers prior to booking.
Site 10 | Medway MC | Internals | Rochester Walk Bundling Centre, Maidstone Road, Rochester ME1 3AU | Nicole Menon | gary.ware@royalmail.com 07841570847 | Use of WBC for Christmas operations, some internal works to take place inculuding the removal and reinstatment of small amounts of racking. Awaiting date. 5/9/23 - awaiting confirmation from RM as to whether this site will be used this year (vs Marquee) 19/9 - likelihood is we will go with the marquee but wil be confirmed on the 21st Sept | RLB | Edmund B |  |  | n/a | n/a | 2023-11-24 | 2024-01-01
Site 11 | ELDC | Internals | Gardeners way, Oliver Road, Grays, RM20 3ED | Tony Fostekew | nick.minden@royalmail.com 07435 761324 | Internal works to make ready for Cross Dock operation. Dock levellers serviced, deep clean and electrics / heating tested and working. Yard may need re-lining and patch repairing, will check on site audit visit. 5/9/23 - scoped and costed, discussion held with PFSL as most of scope is their responsibility. They should be completing by mid oct latest. 11/9 - ELDC approved to proceed, need to revise schedule to exclude works being undertaken by PFSL. 26/9 - awaiting start date from Vinci 3/10/23 - starting 23rd October, 1 week work. 17/10 - starting 23rd Oct, PFSL still working. 24/10 - on site this week, PFSL generally complete, issue with yard area (VOC) having a poor surface, may require more significant work to bring back up to standard - standalone project. | RLB | Phil Swain |  |  |  |  | 2023-11-06 | 2023-12-31 | Queries over maintenance issues - asked LC to confirm if anything has been put through the helpdesk
Site 12 | MK PSC | Internals | Magnitude 314, Magna Park, Fen Street, Milton Keynes, MK17 8EW | Nicky Dunn |  | Un-monthballing of the PSC. Scope visit required. New power supply required for conveyor. - No works for us other than BP45 | RLB | Robbie Brindley

## Accio Marquee
Royal Mail 2023 Peak Programme - Temporary Strucutres - Client Status Update - V16 As at /11/2023
Location & type | Accio Start On Site Date | Accio Completion Date | Hire Period |  | No of Weeks | Property | Postcode | Planner | Status | Comments | Status | PCIP received | Plans Issued | RAM's Issued
|  |  | Request For Service Date | End Of Service Date
Amesbury | NA | NA | On going | 2024-01-01 | on going | 20 London Road, Amesbury, | SP4 7EW | Andy Martin | Run on hire | Extended until 01/01/2024 | 1
Bramhall | NA | NA | On going | 2024-01-28 | on going | Syddal Rd, Bramhall, Stockport, | SK7 1AA | Clare Thomson | Run on hire | Extended until 28/01/2024 | 1
Farnborough | NA | NA | On going | 2024-01-01 | on going | 108 Alexandra Rd, Farnborough, | GU14 6DG | Andy Martin | Run on hire | Extended until 01/01/2024 | 1
Hyde | NA | NA | On going | 2024-01-28 | on going | Hamnett Street, Hyde, | SK14 1AA | Clare Thomson | Run on hire | Extended until 28/01/2024 | 1
Redhill | NA | NA | On going | 2024-03-31 | on going | Redstone Hill, Redhill, | RH1 1AA | Nicole Menon | Run on hire | Extended until 31/04/2024 | 1
Romsey | NA | NA | On going | 2024-01-01 | on going | 15 Church Street, Romsey, | SO51 8XA | Andy Martin | Run on hire | Extended Hire until 01/01/2024 | 1
Southampton 2 | NA | NA | On going | 2024-01-01 | on going | FALSE | SO18 2XX | Andy Martin | Run on hire | Extended Hire until 01/01/2024 | 1
Winterbourne DO Marquee | NA | NA | On going | 2024-02-10 | on going | 22 Bristol Road, Bristol | BS36 1RG | Alan Nicholls | Run on hire | Extended Hire until 10/02/2024 | 1
Tyneside Additional Strucutre | TBC | TBC | TBC | TBC | TBC | Tyneside Mail Centre, Earlsway, Gateshead | NE11 0YY | Anne O'Connor | Requires Scoping or costing | Request from Andy Jenkins at UKRLB | 3
Bude | 2023-11-05 | 2023-11-05 | 2023-11-13 | 2024-02-05 | 12 | Belle View, Bude | EX23 8LU | Alan Nicholls | Instructed | Instructed - No install programme comments | 4
Buxton | 2023-11-13 | 2023-11-14 | 2023-11-20 | 2024-01-01 | 6 | Palace Road, Buxton | SK17 6AB | Clare Thomson | Instructed | Instructed - No install programme comments | 4
Congleton DO | 2023-11-15 | 2023-11-16 | 2023-11-20 | 2024-01-01 | 6 | Unit 9, Greendiel Farm Industrial Estate, Congleton | CW12 4ZZ | Clare Thomson | Instructed | Instructed - No install programme comments | 4
Croydon MC Marquee | 2023-11-11 | 2023-11-18 | 2023-11-20 | 2024-01-05 | 6.5714 | Beddington Farm Road, Croydon | CR9 4AA | Nicole Menon | Instructed | instructed - No install programme comments | 4
Edinburgh | 2023-11-03 | 2023-11-06 | 2023-11-07 | 2024-01-14 | 9.7143 | Cultind Rd | EH11 4YY | Scott Forsyth | Instructed | PM - approved and instructed -04/10/23 | 4
Exeter | 2023-10-30 | 2023-11-04 | 2023-11-06 | 2023-12-31 | 7.8571 | Osprey Road,Sowton Industrial Estate, Exeter | EX2 7XX | Alan Nicholls | Instructed | Instructed - No install programme comments | 4
Inverness | 2023-10-29 | 2023-11-02 | 2023-11-07 | 2024-01-15 | 9.8571 | 7 Strothers Lane, Inverness | IV1 1AA | Scott Forsyth | Instructed | Instructed - No install programme comments | 4
Jubilee MC Marquee | 2023-11-03 | 2023-11-10 | 2023-11-13 | 2024-01-05 | 7.5714 | Godfrey Way, Hounslow | TW4 5XX | Nicky Dunn | Instructed | Instructed - No install programme comments | 4
Nottingham MC Marquee | 2023-10-28 | 2023-11-02 | 2023-11-06 | 2024-01-13 | 9.7143 | Padge Road, Beeston, Nottingham | NG9 2RR | Helen Perry | Instructed | Instructed - No install programme comments | 4
South Midlands | 2023-11-18 | 2023-11-22 | 2023-11-23 | 2024-01-04 | 6 | Swan Valley Way, Northampton, | NN4 9DR | Helen Perry | Instructed | Instructed - No install programme comments | 4
Swindon | 2023-10-29 | 2023-11-05 | 2023-11-06 | 2024-01-02 | 8.1429 | Rowland Hill Close, Swindon | SN3 5TQ | Andy Martin | Instructed | Instructed - Small structure to be installed over the weekend. | 4
Truro | 2023-11-05 | 2023-11-06 | 2023-11-13 | 2023-12-24 | 5.8571 | Newham Industrial Estate, Truro | TR1 1AA | Alan Nicholls | Instructed | Instructed - No install programme comments | 4
Carlisle MC Marquee | 2023-10-20 | 2023-10-27 | 2023-10-30 | 2024-01-01 | 9 | Junction Street, Carlisle | CA1 1AA | Clare Thomson | Instructed | Instructed - No install programme comments | 6
Chelmsford Floor | 2023-10-25 | 2023-10-27 | 2023-10-30 | 2024-01-14 | 10.8571 | Windsford Way, Chelmsford | CM2 5AA | Nicky Dunn | Instructed | Instructed - awaiting confimation of proposed install date | 6
Dorset MC Marquee | 2023-10-25 | 2023-10-29 | 2023-11-06 | 2024-01-06 | 8.7143 | Nuffield Industrial Estate, Poole, Dorset, | BH17 0AA | Alan Nichols | Instructed | Instructed - No install programme comments | 6
Glasgow MC | 2023-09-01 | 2023-09-08 | 2023-09-08 | 2024-01-14 | 18.2857 | 20 Turner Rd, Glasgow | G21 1AA | Scott Forsyth | Instructed | Installed - awaiting update on electric supply to commision electrics. | 6
Medway | 2023-10-28 | 2023-10-28 | 2023-11-13 | 2024-01-12 | 8.5714 | 1 Knight Road, Rochester, | ME2 2EE | Nicole Menon | Instructed | Instructed - No install programme comments | 6
Medway additional Structure | 2023-10-28 | 2023-10-28 | 2023-11-13 | 2024-01-12 | 8.5714 | 1 Knight Road, Rochester, | ME2 2EE | Nicole Menon | Instructed | Instructed - No install programme comments | 6
Romford MC | 2023-10-17 | 2023-10-27 | 2023-10-30 | 2024-01-15 | 11 | Sandgate Close, Romford | RM7 0AB | Nicky Dunn | Instructed | Instructed - No install programme comments | 6
Southampton | 2023-10-20 | 2023-10-24 | 2023-10-31 | 2024-01-08 | 9.8571 | Mitchell Way, Southampton, | SO18 2XX | Andy Martin | Instructed | Instructed - No install programme comments | 6
Swansea | 2023-10-16 | 2023-10-19 | 2023-11-06 | 2023-12-31 | 7.8571 | Siemens Way, Swansea Enterprise Park, Swansea, | SA1 1AA | Alan Nicholls | Instructed | Instructed - No install programme comments | 6
Tyneside | 2023-10-13 | 2023-10-19 | 2023-10-30 | 2024-01-08 | 10 | Tyneside Mail Centre, Earlsway, Gateshead | NE11 0YY | Anne O'Connor | Instructed | Instructed - No install programme comments | 6
Issue History:
V1. - Issued 10-07-23 : Initial information form Paul McGouran and previous year. | [7 empty] | STATUS KEY
V2.- Issued 21-07-23: Information update from Paul Mcgouran 13/07/2023 - confimation of sites not required. Information from Paul Mcgouran 18/07/23 - Carlisle, Chester, | [7 empty] | 1 | Run on
Gateshead and Inverness updated. | [7 empty] | 2 | Requires Scoping or costing
V3 - Issued 04-08-23 : Information updated following 04/08/23 meeting. Haverfordwest no longer required. Paul McGouran email update on 21/07/23: Updated RFS for Manchester and Chester. Amendments made for incorrect Chelmsfor dates. Inverness dates now included. Congleton and Buxton confirmed as not required. | [7 empty] | 3 | Costed and awaiting client feedback
V4 - Issued 11-08-23: 3 site visits taken place, Dorset, Croydon and Gateshead. Costs submitted for S. Midlands, Swindon and Nottigham. Winterbourne, out of PO awaiting clinet instruction. | [7 empty] | 4 | Instructed
V5. - Issued 18-08-23: Redhill , PO runs out at the end of the month, Winterbourne out of PO and awaiting update from Alan Nichols. Dorset options sent out with costs. Glasgow,Inverness and Swansea costs issued. | [7 empty] | 5 | Not mentioned - check whether required
V6.- Issued 25-08-23 : cost issued on Medway and Manchester Bay 9 | [7 empty] | 6 | Complete
V.7 - Issued 01-09-23: Swindon, Truro and Croydon cost issues. Edinburgh and Norwich Dock added for costing. Instructed - Glasgow, Inverness, Chelmsford, Southampton,Exeter, Swansea, Carlisle& Nottingham. | [7 empty] | 7 | Not required
V.7 - Issued 01-09-23: Swindon, Truro and Croydon cost issues. Edinburgh and Norwich Dock added for costing. Instructed - Glasgow, Inverness, Chelmsford, Southampton,Exeter, Swansea, Carlisle& Nottingham. | [7 empty] | 8 | Dismantled and returned to Accio
V.8- Issued 08-09-23: Tyneside cost issued. Instructed - Medway, Dorset. Norwich Dock and Manchester Bay 9 removed.
V.9 - Issued -15/09/23 - Cost issued - Jubilee and Romford. Instructed - Swindon, Truro, Tyneside, Croydon and Dorset. Medway awaitng financial approval. Birmingham removed. Glasgow completed and status changed. South Midlands quote updated.
V.10 - Issued -22/09/23 - cost issued - Edinburgh and Bude. Bude added for costing as per PMs request. Accio installation date populated as per programmme V4. Instructed Jubilee and Medway.
V.11 - Issued -29/09/23 - Instructed: Bude and Romford.
V.12 - Issued -06/10/23 - Instructed: Edinburgh - Cost Issued - Medway additional strucutre.
V.13 - Issued -13/10/23 - No Changes
V.14 - Issued -20/10/23 - Removed: Chester - Cost Issued - Buxton and Congleton. Scoping and costing: Tyneside additional strucutre
V.15 - Issued -20/10/23 - Removed: Chester - Cost Issued - Tyneside additional structure. Instructed: Congleton and Buxton Completed - Romford, Carlisle, Medway, Dorset, Southampton, Chelmsford floor
V.16- Issued -
Formulas:
Hire Period = '[1]2023_'!B51
Hire Period = [Hire Period, row above]

## Parking VOC
ROYAL MAIL XMAS 23/24 - PARKING/VOC'S
REFS | DETAILS | [5 empty] | SURVEYOR |  |  |  | STATUS |  |  |  | OTHER
SEP REF | SITE | Type | ADDRESS | Special Events Planner | Site Contact | Comments | PRACTICE | SURVEYOR 1 | SURVEYOR 2 | Previous Surveyor | LEASE START | LEASE EXPIRY | RFS | LDS | COMMENTS
Site 1 | MSH VOC | VOC | NN6 7DD | Nicky Dunn | 07553381777 & 07 james.h.parker@royalmail.com | MSH USED LAST YEAR TO SUPPORT NDC, THIS YEAR LOOKING TO USE NDC TO SUPPORT MSH - 150 trailers | RLB | Andrew Jenkins |  |  |  |  | 2023-10-02 | 2024-01-29 | Confirmed with N Dunn 1st August that no works required from us on this
Site 2 | Coventry VOC | VOC |  | Nicky Dunn | 07553 379191 Ricki.ravat@royalmail.com | Parking for 50 trailers no units -with security 5/9/23 - site inspected last Friday, was not in the position it should have been in terms of completeness. Due to complete by Mid Oct 11/9/23 - Site visit planned for the 20th, works on site delayed. 26/9 - awaiting confirmation of site visit by LL. POst meeting note - scheduled for 29th Sept. 3/10 - site still not ready, further visit on Friday to review POST MEETING NOTE - discussion held 4th Oct to discuss, will see how Friday goes but there has been a delay in the O-Licence process and also a question as to why they cant just use the NDC - with RM to confirm 17/10 - needs SoC doing, 24/10 - initial SoC done, still works ongoing on site - fencing and lighting will be complete by the end of the week. Final SoC to do. | RLB | Andrew Jenkins |  |  | 2023-10-30 |  | 2023-10-01 | 2024-01-29
Site 3 | Peterlee | VOC |  | Nicky Dunn | 07483135895 & michael.a.salts@royalmail.com | Portacabin - Temporary office, welfare facilities, generator, yard lighting, secure perimeter & even surface of appropriate strength. | RLB | Andrew Jenkins |  |  |  |  | 2023-10-01 | 2024-01-31 | Same site as last year (etained) - no works required
Site 4 | Prestwick Transit House | VOC | Transit House Prestwick airport. KA9 2PL | Nicky Dunn | 07483354160. daniel.wood@royalmail.com | Temporary office, welfare facilities, generator, yard lighting, secure perimeter & even surface of appropriate strength. 5/9/23 - no further works required, in progress 26/9 - RFS date still 16/10. SoC to be undertaken 17/10 - progressing. PMc to check - do we have licence for the VOC yet? 24/10 - prestwick VOC and OH complete barring dock leveller that PFSL looking at, IT going on this week 31/10 No works. RFS | AECOM | Derek Penny | Abi Akinyemi |  |  |  | 2023-10-16 | 2024-01-31 | Scoping visit completed, Trios attended
Site 5 | SDC VOC | VOC | Netherdale road, Wishaw ML2 0ER | Nicky Dunn | 07483354160. daniel.wood@royalmail.com | Yard only and lighting 5/9/23 - budget figures given to RM, awaiting confirmation of whether it is to proceed. 11/9/23 - awaiting parking plan and SoW from AECOM. Needs pricing but site is proceeding 19/9 - approved to proceed. 26/9 - awaiting start date. 3/10/23 - looking to start 17th Oct, to confirm with RM. 2 to 3 days of work POST MEETING NOTE - RM aiming to aquire site on 17th - may want to push back Trios a day. 17/10 - Trios being lined up for next Monday. 24/10 - prestart held, awaiting start date. 31/11 Works complete | AECOM | Derek Penny | Abi Akinyemi |  | 2023-10-16 |  | 2023-10-16 | 2024-01-31 | Scoping inspection arranged 25/07/2023 - site not suitable. New site being looked at - Netherdale Road, Wishaw
Site 6 | Edinburgh VOC | VOC | Royal Highland Showground EH28 8NB | Nicky Dunn | 07423 452900 michael.mcleod@royalmail.com | Yard only and lighting 5/9/23 - sites not suitable, looking for alternatives. 11/9/23 - potential new site found, may need visit 18/9 - site visit to new Gilmarton Site required 26/9 - site visit undertaken, awaiting feedback. Likelihood is that if royal Highland is accpeptable then we will go there instead of Gilmarton 3/10/23 - looking at RHS now, outline parking plan issued 17/10 - still progressing, licence c.23rd Oct. 24/10 - no further work required. | AECOM | Derek Penny | Abi Akinyemi |  |  |  | 2023-10-16 | 2024-01-31 | New sites being looked at on 23/8 - the Wisp and Gilmarton Station Road
Site 7 | Warrington Rail Terminal | VOC | Warrington Rail Terminal, Eagles Park Drive, Winick Quay, Warrington, WA2 8AA | Nicky Dunn | 07725826858 steven.grey@royalmail.com | Remarking the yard at Warrington Rail Terminal would give an additional 45 unit and 30 trailer parking spaces to support NW Hub VOC peak requirement. The rail terminal is an existing RM site with an O'License of 22 trailers currently. Remarking would allow this to increase considerably. 5/9/23 - likelihood is that we will proceed with line marking at this site. Site plan done pending queries, meeting on 6/9 to sign off/instruct 11/9/23 - confirmed this site is the one to proceed. SoW and price required to enable us to instruct. Must be completed ASAP. 19/9 - scoped and awaiting Trios price 26/9 - approved to proceed, awaiting start date 3/10/23 - awaiting start date. PCI & PAP done, awaiting CPP etc 17/10 - starting on 23rd, everything else OK. 24/10 - started this week, due to complete next. 31/10 On site. Weather holding up line marking | JYM | Stuart Baird |  |  |  |  | Early November | End of Jan 2024
Site 8 | Warrington Mail Centre | VOC | Kammac Dallam Lane, Warrington | Nicky Dunn | 07725826858 steven.grey@royalmail.com | We are currently progressing a business case to utilise some of the staff car park at Warrington MC to increase the parking for WAVOC (part of NW Hub VOC based at Warrington Mail Centre). The costs for this are significant so if we cannot secure the authority and progress the works in time for peak, we will have a requirement for additional trailer parking. If the works do go ahead and are completed, Warrington MC Plant Manager has flagged a risk for staff car parking for peak which will need to be factored in to the overall capacity needed (for the VOC and the plant) 31/7/23 - now looking at Kammac site in Warrington 5/9/23 - Kammac site likely aborted in leiu of Rail Terminal 11/9/23 - site aborted | JYM | Stuart Baird |  |  |  |  | Ready for Service by October 2023 | End of Jan 2024 | Still waiting for overall demise to be confirmed by EM to enable scope to be finalised and costed (Steve Grey). | XXXX
Site 9 | Northern Ireland | VOC | Ballycraigy Business Park, 655 Antrim Road, Mallusk, BT36 4RG | Nicky Dunn | 07553375334 james.ferguson@royalmail.com | Parking is required to support additional trailers at peak health and safety is a major issue on site due to space constraints and is not appropriate for peak operation , same site as 2022 is desireble. Awaiting date from RM. 5/9/23 - Costs received, OK to proceed. 26/9 - TK to check Kingsway have PO. 3/10 - PO in system, TK has chased. Hugh checking on contractor availability 17/10 - PO recieved, starting on 30th. 24/10 - due to start next week. | AECOM | Hugh O'kane |  |  | 2023-10-30 | 2024-01-26 | 2023-10-30 | 2024-01-26
Site 10 | Leeds | VOC | Linkways, Skelton Grange Road, Stourton Leeds LS10 1RZ | Nicky Dunn | 07872 636310 steve.z.thompson@royalmail.com | YDC VOC currently have a year round BAU 2nd VOC located in Leeds next to the fleet workshop. To accommodate the peak requirement, we have the option to acquire and additional acre at the 2nd VOC. It is unknown if the landlord would accommodate RM acquiring the additional acre for a temporary period or whether we would need to commit to a longer lease. The additional acre at the 2nd VOC is the preferred option as it would not require any additional managerial/admin staffing to the BAU 2nd VOC. This would provide additional capacity of circa 20 MUs and 20 trailers 5/9/23 - proceeding with solicitors, drawing recd?? 11/9/23 - awaiting drawing? Cost OK but portaloos need to be funded by site as BAU 26/9 - awaiting start date from Trios, post meeting note - query over O-licence drawing, Matt H to resolve once we hear from RM 3/10 - MH to update ASAP. 17/10 - Trios instructed, minor work. 24/10 - awaiting completion with legals | RLB | Andrew Jenkins |  |  | 2023-10-01 |  | Ready for Service by October 2023 | End of Jan 2024 | Moving of heras fencing, very minimal works
Site 11 | SWDC VOC | VOC | Plot 9000, Severnbanks (same as last year) | Tony Fostekew | 07912426802 peter.x.hicks@royalmail.com | Yard & temp office required (no warehouse). Costs returned. 5/9/23 - proceeding, minor query on electrical costs. 12/9/23 - approved to proceed, awaiting confirmation of acces date and programme from Vinci 26/9 - awaiting programme from Vinci, GJ confirmed Vinci had placed orders at risk pending PO 3/10/23 - outline programme issued, starting on 9th - RM to confirm POST MEETING NOTE - works starting 11th. 17/10 - barring lighting, everything else complete. Some potholes on site that may need rectifying, lighting to be installed on 30th Oct. 24/10 - lighting going in on the 30th. LRA awaited. 31/10 Lighting on site Monday. Awaiting PAT test and cabin elec cert | KKS | Sarah Palmer |  |  | 2023-10-02 |  | 2023-10-02 | 2024-01-26
Site 12 | HWDC VOC | VOC |  | Tony Fostekew | 07736786689 danny.moran@royalmail.com | Yard & temp office required (no warehouse). Awaiting costs by end of week. 5/9/23 - site search ongoing, alternative hardstanding area possible but awaiting confirmation as to whether this sole use for RM 26/9 - alternative site being surveyed 3/10/23 - alternative surveyed, may have been let. Further alternative being surveyed 3/10/23 17/10 - Scope issued and parking plan issued. Pricing to be chased up. Schedule of condition to be issued by end of week. Chubb and LRA lined up 24/10 - still awaiting costs. 31/10 Ongoing. Taking on site 01/11. Unsure of date of site set up | KKS | Mark Hole |  |  | 2023-10-02 |  | 2023-10-02 | 2024-01-26
Site 13 | PRDC VOC | VOC | Willen Field Road, London, NW10 7BQ | Tony Fostekew | 07801 093728 ricky.archer@royalmail.com | Parking for HGV powered untis and trailers, site office facilities and welfare. Costs back by end of week. 5/9/23 - Carey Way looking to move forward on, drawing issued, need to agree 11/9/23 - proceeding, costs approved. Need landlords certification & records, arrange FRA etc 18/9 - RM still awaiting agreement of HoT's - we can still go ahead and arrange surveys etc as needed 26/9 - HoT's progressing, awaiting programme from Vinci. RM checking whether we can get in to site prior to licence date to undertake work 3/10/23 - potential start on site on the 19th October - will we have the site by then? POST MEETING NOTE - This one has not gone to lawyers as yet. HoTs have been agreed however, O licence has not been signed as yet, depends on whether the landlords sign the O licence this week. 17/10 - SoW will be issued to Vinci for pricing. Plan for O-licence has gone in. Need to check on welfare requirements 24/10 - welfare confirmed that they will only need a welfare van - add to BP45. Site clearance ongoing. SoW and Soc to undertake. 31/10 - Welfare van for security. Scoping m,eeting 03/11 with Vinci. | RLB | Phil Swain |  |  | 2023-11-13 |  | 2022-11-14 | 2023-01-31 | Atlas Road looked at originally, now looking at Carey Way which is the preferred site - landlord subsequently has come back saying they will offer an 18 month lease.
Site 14 | ELDC - dual use with ADM C East | VOC | Gardeners way, Oliver Road, Grays, RM20 3ED | Tony Fostekew | 07801 093728 ricky.archer@royalmail.com | Parking for HGV powered untis and trailers, site office facilities and welfare 3/10/23 - Phil visiting site on 4th to check on PFSL progress 31/10 Variation to increase tarmac. 6/11 to complete these works | RLB | Phil Swain |  |  |  |  | 2022-11-14 | 2023-01-31
Site 15 | ELDC | VOC | Gardeners way, Oliver Road, Grays, RM20 3ED | Tony Fostekew | 07793 584063 martin.carr@royalmail.com | Extention to exisiting BAU for a further 60 Mu's and 50 trailer spaces | RLB | Phil Swain |  |  |  |  | 2023-10-02 | 2024-01-07

## PFW
ROYAL MAIL XMAS 23/24 - PARCELFORCE | [44 empty] | Updated 12th September
REFS |  | DETAILS | [5 empty] | SURVEYOR |  |  |  | STATUS |  |  |  | SCHEDULE OF CONDITION |  | SCOPE OF WORKS | [5 empty] | HEALTH & SAFETY |  |  |  | FINANCES | [8 empty] | PROGRAMME |  |  |  | SITE - KEY DATES OF ATTENDANCE |  |  |  | OTHER
[28 empty] | WORKS |  |  |  | FEES
SEP REF | L CATON REF | SITE | Type | ADDRESS | Special Events Planner | Site Contact | Comments | PRACTICE | SURVEYOR 1 | SURVEYOR 2 | Previous Surveyor | LEASE START | LEASE EXPIRY | RFS | LDS | INSPECTION | ISSUED | INSPECTION | ISSUED | SCOPE APPROVED BY PFW | PRICE RETURNED | RM APPROVED | INSTRUCTED | ASBESTOS SURVEY | ASBESTOS R&D | PCI | CPP REVIEWED | VINCI / TRIOS | ACCIO | CHUBB | OTHER | PAP | L8 LRA | PUWER | FRA | OTHER | COMMENCEMENT ON SITE | HANDOVER DATE | DILAPS START | DILAPS END | CHUBB | L8 RISK ASSESSMENT | SITE LOG BOOK | FIRE RISK ASSESSMENT | COMMENTS
Note on B4: Paul McGouran: Applies to OH, Parking, VOC sites
Note on AF4: Paul McGouran: Add details as a comment
Note on AK4: Paul McGouran: Add details as a comment
Note on AL4: Paul McGouran: Add planned start if not commenced
Note on AM4: Paul McGouran: Add planned date if not complete
Note on C5: Paul McGouran: Might be a temp unit / Outhouse - confirm with SEP