## Outhouses
ROYAL MAIL XMAS 23/24 - OUTHOUSES
REFS | DETAILS |  |  |  |  | SURVEYOR |  |  |  | STATUS
SEP REF | SITE | Type | ADDRESS | Special Events Planner | Site Contact | PRACTICE | SURVEYOR 1 | SURVEYOR 2 | Previous Surveyor | LEASE START | LEASE EXPIRY | RFS | LDS
Site 1 | Bristol MC | Outhouse | TBC | Alan Nicholls | 07802 928683 robert.j.paterson@royalmail.com | KKS | Glyn Jones |  |  |  |  | 2023-10-31 | 2024-01-28
Site 3 | South East PSC | Outhouse | Tetris Rockware Avenue Greenford UB6 0AD | Andrew Martin | furat.muhi-al-din@royalmail.com 07841 466245 | RLB | Robbie Brindley |  |  | Ongoing |  | 2023-11-06 | 1st week in Jan, then decommission - 14th Jan
Site 4 | Manton | Outhouse | Unit 4 Manton Wood Retford Road Manton Wood Enterprise Park Worksop S80 2RS | Anne O'Connor | Ian.J.Brown@royalmail.com 07802791840 | RLB | Andrew Jenkins |  |  | Ongoing |  | RFS by end of Oct 2023 | 2024-01-08
Site 5 | Tyneside OH | Outhouse |  | Anne O'Connor | 07889929494 philip.welsh@royalmail.com | RLB | Andrew Jenkins |  |  |  |  | 2023-10-30 | 2024-01-08
Site 6 | South Midlands Plant | Outhouse | Royal Mail Northampton PSC Unit 5 Panattoni Park Weedon Road NORTHAMPTON NN7 4DE *Same space needed as for 2022* | Helen Perry | mohammad.s.rahman@royalmail.com 07553 367512 | RLB | Andrew Jenkins |  |  | Ongoing |  | 2023-10-09 | 2024-01-20
Site 7 | East of Scotland Outhouse | Outhouse | Royal Highland | Scott Forsyth | 07736 786332 david.condon@royalmail.com | AECOM | Derek Penny | Abi Akinyemi | Derek Penny | 24/11/23 | 28/1/24 | 2023-11-07 | 2024-01-14
Site 8 | Prestwick Outhouse | Outhouse | Prestwick Airport, Transit House, KA9 2QA | Scott Forsyth | graeme.turnbull@roiyalmail.com 07568 564429 | AECOM | Derek Penny | Abi Akinyemi | Scott Graham | Ongoing |  | 2023-11-07 | 2024-01-14
Site 9 | Norwich MC Outhouse | Outhouse | Former Tuffnells Depot, 23 Vulcan Rd S, Norwich NR6 6AG | Nicky Dunn | 07841568085 angela.travis@royalmail.com | RLB | Robbie Brindley |  |  | 2023-10-24 |  | 2023-11-14 | 2023-12-31

## Internals
ROYAL MAIL XMAS 23/24 - INTERNALS
REFS | DETAILS |  |  |  |  | SURVEYOR |  |  |  | STATUS
SEP REF | SITE | Type | ADDRESS | Special Events Planner | Site Contact | PRACTICE | SURVEYOR 1 | SURVEYOR 2 | Previous Surveyor | LEASE START | LEASE EXPIRY | RFS | LDS
Site 1 | Cardiff MC | Internals | Cardiff Mail Centre, 220-228 Penarth Road, Cardiff, CF11 8TA | Alan Nicholls | 07850 815888 andrew.colclough@royalmail.com | KKS |  |  |  | n/a | n/a | 2023-11-27 | 2023-12-24
Site 2 | Exeter MC | Internals | Exeter Mail Centre, Osprey Road, Sowton Industrial Estate, Exeter, EX2 7XX | Alan Nicholls | 07909 212756 ian.percival@royalmail.com | KKS |  |  |  | n/a | n/a | 2023-11-06 | 2023-12-31
Site 3 | Exeter MC | Internals | Exeter Mail Centre, Osprey Road, Sowton Industrial Estate, Exeter, EX2 7XX | Alan Nicholls | 07909 212756 ian.percival@royalmail.com | KKS |  |  |  | n/a | n/a | 2023-11-06 | 2023-12-31
Site 4 | Gloucester M.C | Internals | Gloucester Mail Centre, Eastern Ave, Gloucester, GL4 3AA | Alan Nicholls | 07872 004928 alan.r.nicholls@royalmail.com | KKS |  |  |  | n/a | n/a | 2023-11-06 | 2023-12-24
Site 5 | South Wales / West PSC | Internals | South West PSC, Ty-Glas, Llanishen, Cardiff, CF14 5DU | Alan Nicholls | 07872 004928 alan.r.nicholls@royalmail.com | KKS |  |  |  | n/a | n/a | 2023-11-06 | 2023-12-24
Site 6 | South Midlands Plant | Internals | Royal Mail South Midlands Swan Valley Way NORTHAMPTON NN4 9DR | Helen Perry | mohammad.s.rahman@royalmail.com 07553 367512 | RLB | Andrew Jenkins |  |  | n/a | n/a | 2023-11-20 | 2023-12-24
Site 7 | Chelmsford MC Internal | Internals | Winsford Way, Springfield, Chelmsford CM2 5AA | Nicky Dunn | nick.j.dent@royalmail.com | RLB | Seb Hathaway |  |  | n/a | n/a | 30/10 for floating floor 20/11 frames operational | 2024-01-14
Site 8 | DQ Northern Ireland Internal | Internals | Tomb Street BT1 1AA | Nicky Dunn | mark.magee@royalmail.com 07553388341 | AECOM | Hugh O'Kane |  |  | n/a | n/a | 13/11/2023 | 29/03/2024
Site 9 | Aberdeen MC Basement | Internals | Aberdeen Mail Centre, Wellington Circle, Aberdeen, AB12 3TT | Scott Forsyth | david.i.noble@royalmail.com 07436 033191 | AECOM | Derek Penny | Abi Akinyemi | N/A | n/a | n/a | 2023-11-07 | 2024-01-20
Site 10 | Medway MC | Internals | Rochester Walk Bundling Centre, Maidstone Road, Rochester ME1 3AU | Nicole Menon | gary.ware@royalmail.com 07841570847 | RLB | Edmund B |  |  | n/a | n/a | 2023-11-24 | 2024-01-01
Site 11 | ELDC | Internals | Gardeners way, Oliver Road, Grays, RM20 3ED | Tony Fostekew | nick.minden@royalmail.com 07435 761324 | RLB | Phil Swain |  |  |  |  | 2023-11-06 | 2023-12-31
Site 12 | MK PSC | Internals | Magnitude 314, Magna Park, Fen Street, Milton Keynes, MK17 8EW | Nicky Dunn |  | RLB | Robbie Brindley

## Accio Marquee
Royal Mail 2023 Peak Programme - Temporary Strucutres - Client Status Update - V16 As at /11/2023
Location & type | Accio Start On Site Date | Accio Completion Date | Hire Period |  | No of Weeks | Property | Postcode | Planner | Status | Status | PCIP received | Plans Issued | RAM's Issued
|  |  | Request For Service Date | End Of Service Date
Amesbury | NA | NA | On going | 2024-01-01 | on going | 20 London Road, Amesbury, | SP4 7EW | Andy Martin | Run on hire | 1
Bramhall | NA | NA | On going | 2024-01-28 | on going | Syddal Rd, Bramhall, Stockport, | SK7 1AA | Clare Thomson | Run on hire | 1
Farnborough | NA | NA | On going | 2024-01-01 | on going | 108 Alexandra Rd, Farnborough, | GU14 6DG | Andy Martin | Run on hire | 1
Hyde | NA | NA | On going | 2024-01-28 | on going | Hamnett Street, Hyde, | SK14 1AA | Clare Thomson | Run on hire | 1
Redhill | NA | NA | On going | 2024-03-31 | on going | Redstone Hill, Redhill, | RH1 1AA | Nicole Menon | Run on hire | 1
Romsey | NA | NA | On going | 2024-01-01 | on going | 15 Church Street, Romsey, | SO51 8XA | Andy Martin | Run on hire | 1
Southampton 2 | NA | NA | On going | 2024-01-01 | on going | FALSE | SO18 2XX | Andy Martin | Run on hire | 1
Winterbourne DO Marquee | NA | NA | On going | 2024-02-10 | on going | 22 Bristol Road, Bristol | BS36 1RG | Alan Nicholls | Run on hire | 1
Tyneside Additional Strucutre | TBC | TBC | TBC | TBC | TBC | Tyneside Mail Centre, Earlsway, Gateshead | NE11 0YY | Anne O'Connor | Requires Scoping or costing | 3
Bude | 2023-11-05 | 2023-11-05 | 2023-11-13 | 2024-02-05 | 12 | Belle View, Bude | EX23 8LU | Alan Nicholls | Instructed | 4
Buxton | 2023-11-13 | 2023-11-14 | 2023-11-20 | 2024-01-01 | 6 | Palace Road, Buxton | SK17 6AB | Clare Thomson | Instructed | 4
Congleton DO | 2023-11-15 | 2023-11-16 | 2023-11-20 | 2024-01-01 | 6 | Unit 9, Greendiel Farm Industrial Estate, Congleton | CW12 4ZZ | Clare Thomson | Instructed | 4
Croydon MC Marquee | 2023-11-11 | 2023-11-18 | 2023-11-20 | 2024-01-05 | 6.5714 | Beddington Farm Road, Croydon | CR9 4AA | Nicole Menon | Instructed | 4
Edinburgh | 2023-11-03 | 2023-11-06 | 2023-11-07 | 2024-01-14 | 9.7143 | Cultind Rd | EH11 4YY | Scott Forsyth | Instructed | 4
Exeter | 2023-10-30 | 2023-11-04 | 2023-11-06 | 2023-12-31 | 7.8571 | Osprey Road,Sowton Industrial Estate, Exeter | EX2 7XX | Alan Nicholls | Instructed | 4
Inverness | 2023-10-29 | 2023-11-02 | 2023-11-07 | 2024-01-15 | 9.8571 | 7 Strothers Lane, Inverness | IV1 1AA | Scott Forsyth | Instructed | 4
Jubilee MC Marquee | 2023-11-03 | 2023-11-10 | 2023-11-13 | 2024-01-05 | 7.5714 | Godfrey Way, Hounslow | TW4 5XX | Nicky Dunn | Instructed | 4
Nottingham MC Marquee | 2023-10-28 | 2023-11-02 | 2023-11-06 | 2024-01-13 | 9.7143 | Padge Road, Beeston, Nottingham | NG9 2RR | Helen Perry | Instructed | 4
South Midlands | 2023-11-18 | 2023-11-22 | 2023-11-23 | 2024-01-04 | 6 | Swan Valley Way, Northampton, | NN4 9DR | Helen Perry | Instructed | 4
Swindon | 2023-10-29 | 2023-11-05 | 2023-11-06 | 2024-01-02 | 8.1429 | Rowland Hill Close, Swindon | SN3 5TQ | Andy Martin | Instructed | 4
Truro | 2023-11-05 | 2023-11-06 | 2023-11-13 | 2023-12-24 | 5.8571 | Newham Industrial Estate, Truro | TR1 1AA | Alan Nicholls | Instructed | 4
Carlisle MC Marquee | 2023-10-20 | 2023-10-27 | 2023-10-30 | 2024-01-01 | 9 | Junction Street, Carlisle | CA1 1AA | Clare Thomson | Instructed | 6
Chelmsford Floor | 2023-10-25 | 2023-10-27 | 2023-10-30 | 2024-01-14 | 10.8571 | Windsford Way, Chelmsford | CM2 5AA | Nicky Dunn | Instructed | 6
Dorset MC Marquee | 2023-10-25 | 2023-10-29 | 2023-11-06 | 2024-01-06 | 8.7143 | Nuffield Industrial Estate, Poole, Dorset, | BH17 0AA | Alan Nichols | Instructed | 6
Glasgow MC | 2023-09-01 | 2023-09-08 | 2023-09-08 | 2024-01-14 | 18.2857 | 20 Turner Rd, Glasgow | G21 1AA | Scott Forsyth | Instructed | 6
Medway | 2023-10-28 | 2023-10-28 | 2023-11-13 | 2024-01-12 | 8.5714 | 1 Knight Road, Rochester, | ME2 2EE | Nicole Menon | Instructed | 6
Medway additional Structure | 2023-10-28 | 2023-10-28 | 2023-11-13 | 2024-01-12 | 8.5714 | 1 Knight Road, Rochester, | ME2 2EE | Nicole Menon | Instructed | 6
Romford MC | 2023-10-17 | 2023-10-27 | 2023-10-30 | 2024-01-15 | 11 | Sandgate Close, Romford | RM7 0AB | Nicky Dunn | Instructed | 6
Southampton | 2023-10-20 | 2023-10-24 | 2023-10-31 | 2024-01-08 | 9.8571 | Mitchell Way, Southampton, | SO18 2XX | Andy Martin | Instructed | 6
Swansea | 2023-10-16 | 2023-10-19 | 2023-11-06 | 2023-12-31 | 7.8571 | Siemens Way, Swansea Enterprise Park, Swansea, | SA1 1AA | Alan Nicholls | Instructed | 6
Tyneside | 2023-10-13 | 2023-10-19 | 2023-10-30 | 2024-01-08 | 10 | Tyneside Mail Centre, Earlsway, Gateshead | NE11 0YY | Anne O'Connor | Instructed | 6
Formulas:
Hire Period = '[1]2023_'!B51
Hire Period = [Hire Period, row above]

## Parking VOC
ROYAL MAIL XMAS 23/24 - PARKING/VOC'S
REFS | DETAILS |  |  |  |  | SURVEYOR |  |  |  | STATUS
SEP REF | SITE | Type | ADDRESS | Special Events Planner | Site Contact | PRACTICE | SURVEYOR 1 | SURVEYOR 2 | Previous Surveyor | LEASE START | LEASE EXPIRY | RFS | LDS
Site 1 | MSH VOC | VOC | NN6 7DD | Nicky Dunn | 07553381777 & 07 james.h.parker@royalmail.com | RLB | Andrew Jenkins |  |  |  |  | 2023-10-02 | 2024-01-29
Site 2 | Coventry VOC | VOC |  | Nicky Dunn | 07553 379191 Ricki.ravat@royalmail.com | RLB | Andrew Jenkins |  |  | 2023-10-30 |  | 2023-10-01 | 2024-01-29
Site 3 | Peterlee | VOC |  | Nicky Dunn | 07483135895 & michael.a.salts@royalmail.com | RLB | Andrew Jenkins |  |  |  |  | 2023-10-01 | 2024-01-31
Site 4 | Prestwick Transit House | VOC | Transit House Prestwick airport. KA9 2PL | Nicky Dunn | 07483354160. daniel.wood@royalmail.com | AECOM | Derek Penny | Abi Akinyemi |  |  |  | 2023-10-16 | 2024-01-31
Site 5 | SDC VOC | VOC | Netherdale road, Wishaw ML2 0ER | Nicky Dunn | 07483354160. daniel.wood@royalmail.com | AECOM | Derek Penny | Abi Akinyemi |  | 2023-10-16 |  | 2023-10-16 | 2024-01-31
Site 6 | Edinburgh VOC | VOC | Royal Highland Showground EH28 8NB | Nicky Dunn | 07423 452900 michael.mcleod@royalmail.com | AECOM | Derek Penny | Abi Akinyemi |  |  |  | 2023-10-16 | 2024-01-31
Site 7 | Warrington Rail Terminal | VOC | Warrington Rail Terminal, Eagles Park Drive, Winick Quay, Warrington, WA2 8AA | Nicky Dunn | 07725826858 steven.grey@royalmail.com | JYM | Stuart Baird |  |  |  |  | Early November | End of Jan 2024
Site 8 | Warrington Mail Centre | VOC | Kammac Dallam Lane, Warrington | Nicky Dunn | 07725826858 steven.grey@royalmail.com | JYM | Stuart Baird |  |  |  |  | Ready for Service by October 2023 | End of Jan 2024 | XXXX
Site 9 | Northern Ireland | VOC | Ballycraigy Business Park, 655 Antrim Road, Mallusk, BT36 4RG | Nicky Dunn | 07553375334 james.ferguson@royalmail.com | AECOM | Hugh O'kane |  |  | 2023-10-30 | 2024-01-26 | 2023-10-30 | 2024-01-26
Site 10 | Leeds | VOC | Linkways, Skelton Grange Road, Stourton Leeds LS10 1RZ | Nicky Dunn | 07872 636310 steve.z.thompson@royalmail.com | RLB | Andrew Jenkins |  |  | 2023-10-01 |  | Ready for Service by October 2023 | End of Jan 2024
Site 11 | SWDC VOC | VOC | Plot 9000, Severnbanks (same as last year) | Tony Fostekew | 07912426802 peter.x.hicks@royalmail.com | KKS | Sarah Palmer |  |  | 2023-10-02 |  | 2023-10-02 | 2024-01-26
Site 12 | HWDC VOC | VOC |  | Tony Fostekew | 07736786689 danny.moran@royalmail.com | KKS | Mark Hole |  |  | 2023-10-02 |  | 2023-10-02 | 2024-01-26
Site 13 | PRDC VOC | VOC | Willen Field Road, London, NW10 7BQ | Tony Fostekew | 07801 093728 ricky.archer@royalmail.com | RLB | Phil Swain |  |  | 2023-11-13 |  | 2022-11-14 | 2023-01-31
Site 14 | ELDC - dual use with ADM C East | VOC | Gardeners way, Oliver Road, Grays, RM20 3ED | Tony Fostekew | 07801 093728 ricky.archer@royalmail.com | RLB | Phil Swain |  |  |  |  | 2022-11-14 | 2023-01-31
Site 15 | ELDC | VOC | Gardeners way, Oliver Road, Grays, RM20 3ED | Tony Fostekew | 07793 584063 martin.carr@royalmail.com | RLB | Phil Swain |  |  |  |  | 2023-10-02 | 2024-01-07